## Schedule_Activities
activity_id | name | wbs_id | baseline_duration_days | remaining_duration_days | calendar_id | status | predecessors
A100 | Design | 1.1 | 30 | 30 | standard_5_day | not_started
A200 | Procurement | 1.2 | 60 | 60 | standard_5_day | not_started | A100
A300 | Construction | 1.3 | 90 | 90 | standard_5_day | not_started | A200
A400 | Testing | 1.4 | 20 | 20 | standard_5_day | not_started | A300

## Schedule_Uncertainty
activity_id | distribution | minimum | most_likely | maximum
A100 | triangular | 25 | 35 | 50
A200 | triangular | 50 | 70 | 110
A300 | triangular | 80 | 100 | 150
A400 | triangular | 15 | 25 | 45

## Cost_Estimate
cost_id | wbs_id | description | baseline_cost | cost_type | currency
C100 | 1.1 | Design labor | 500000 | duration_dependent | USD
C200 | 1.2 | Equipment | 2500000 | fixed | USD
C300 | 1.3 | Construction labor | 4000000 | duration_dependent | USD
C400 | 1.0 | Project management | 75000 | monthly_burn | USD

## Cost_Uncertainty
cost_id | distribution | minimum | most_likely | maximum
C100 | triangular | 450000 | 525000 | 700000
C200 | triangular | 2300000 | 2500000 | 3000000
C300 | triangular | 3500000 | 4200000 | 5200000

## Cost_Schedule_Map
mapping_id | cost_id | activity_id | behavior
MAP-001 | C100 | A100 | scale_with_duration
MAP-002 | C200 | A200 | fixed_to_activity
MAP-003 | C300 | A300 | scale_with_duration
MAP-004 | C400 | A100 | project_burn
MAP-005 | C400 | A200 | project_burn
MAP-006 | C400 | A300 | project_burn
MAP-007 | C400 | A400 | project_burn

## Risk_Register
risk_id | name | description | probability | owner | status
R100 | Design rework | Design review may require rework | 0.25 | Engineering | active
R200 | Supplier delay | Supplier fabrication may be late | 0.3 | Procurement | active
R300 | Field productivity loss | Field work may underperform | 0.35 | Construction | active

## Risk_Impacts
impact_id | risk_id | activity_id | cost_id | min_delay | most_likely_delay | max_delay | min_cost | most_likely_cost | max_cost
RI-001 | R100 | A100 | C100 | 10 | 20 | 30 | 100000 | 250000 | 400000
RI-002 | R200 | A200 | C200 | 20 | 40 | 60 | 200000 | 500000 | 800000
RI-003 | R300 | A300 | C300 | 15 | 30 | 45 | 500000 | 900000 | 1500000

## Assumptions
assumption_id | assumption | applies_to | impact_if_wrong
A-001 | No major scope change after design freeze | Engineering | Could create rework